## Sheet1
| 2023-03-23 | 2023-04-23 | 2023-05-23 | 2023-06-23 | 2023-07-23 | 2023-08-23 | 2023-09-23 | 2023-10-23 | 2023-11-23 | 2023-12-23 | 2023-01-24 | 2023-02-24 | 2023-03-24
Develop and deploy self-report readiness assessment template and synthesize results
Decide on scope of services and EBP list
Develop certification documents and process
Develop and deploy community needs assessment and incorporate into certification documents/processes
Conduct initial site visits in response to results from self-report readiness assessments
Conduct programming/certification listening sessions around programming with 4 current CCBHCs
Conduct listening sessions around 5B CQI plans with 4 current CCBHCs
Facilitate measure development process to obtain broader CSB review and feedback on quality mesures
Develop technical specs for quality measures (depending upon SAMHSA releasing updated guidance)
Finalize quality measures
Provide TA, consultation, and/or training re: CQI plans
Develop PPS methodology
Develop PPS cost reports
Certify CCBHCs (Jan. 2025 - July 2025)