## Slide 1: Enterprise Investment Board
November’s Monthly Meeting

## Slide 2
Establish Quorum
Review Action Items
EPMO Recommendations
Q&A Interactive Session
Appendix – Project Health
Agenda

## Slide 3: Intake Pipeline (28)
ITIB Submissions (8)
ObservSMART
Elavon (electronic payments)
Web Portal for Marcus Alerts
Facilities Enterprise Human Resource System Solution (formerly HOPS HR)
Fiscal Note/Fireside Chat
COTS FOIA
EDCC Integration
Discharge Assistance Planning
Potential Future Projects List
EIB Submissions (10)
UKG Dimensions/Pro - Migration and Implementation
VCBR Cashless Payment
Facilities Clocks & Badges Replacement
Telehealth Services for facilities
OSVP Database
Patient Id Armband Integrated Solution
Language Interpretation & Translation (contract expiring 10/31)
CSH Athelas Clozaril PoC Test
ePrescribe Discharge Medication Billing
Financial Management System Replacement
Pending Intake Submission (7)
Tickit Health
EHR – ADC and Integration w/ EHR Catawba and SEVTC
MART Scheduler
EHR - OnePlan
EHR - Expand glucometer and vital signs projects to additional facilities
Update legal status code in Avatar
Sensei (contract renewal)
Grandfathered in – No Intake Form (3):
AAIDD/Supports Intensity Scale
Counter Tools
VA Navigator

## Slide 4: Next Step – Close
Community
Clinical/Facilities
N/A
Operations
N/A
N/A
Recommendations to Close

## Slide 5: Next Step – Approve for Project
Community
Not Ready
Clinical/Facilities
Not Ready
Operations
Not Ready​
Recommendations to Project

## Slide 6: In Progress - Business Case Development
Community
N/A
Clinical/Facilities
Language Interpretation & Translation Solution – M
Operations
Telehealth Services -S
COTS FOIA - S
Facilities Clocks & Badges Replacement - S
Progress Update
Unfunded, per ITIB intake form
Included in IT Strategic Plan

## Slide 7: As time permits –Business Case Development
Community
N/A
Clinical/Facilities
UKG Dimensions/Pro Migration & Implementation
Operations
EDCC Integration / ​Smartchart Network – M
Athelas Clozaril Point of Care Test (CSH) – M
Patient ID Armband Integrated Solution
Discharge Assistance Planning (DAP) – L ObservSMART – L
EPMO Pipeline Backlog
Unfunded, per intake form
Included in IT Strategic Plan

## Slide 8: Next Step – Start Business Case Development
Community
None
Clinical/Facilities
Cashless Payment Solution (VCBR)
Operations
Enterprise Human Resource Information System Solution
Elavon (electronic payments)
OSVP Database
Fiscal Note/Fireside Chat
EPMO Pipeline Backlog
Unfunded, per intake form
Included in IT Strategic Plan

## Slide 9: Next Step – Pre-EIB Request Review
Community
None
Clinical/Facilities
ePrescribe Discharge Medication Billing
Operations
Financial Management System
Intakes Submitted After EIB Deadline
Unfunded, per intake form
Included in IT Strategic Plan

## Slide 10: December EIB Meeting Tuesday, 12/12/2023
11/16/2023 EIB Submission Form Deadline
11/29/2023 EIB / Data Modernization Program Sync Up w/Kathleen Graham
        Review new intakes submitted across the agency for data modernization program alignment (to pursue great on future state vs better on current state)
11/29/2023 EIB Priority List for Dec EIB (Community) w/Craig Camidge and Jean Dailey (on leave)
12/1/2023 EIB Priority List for Dec EIB (Facilities/Clinical) w/Lauren Cartwright and Charles Mathenge
11/29/2023 EIB Priority List for Dec EIB (Operations) w/Russell Accashian and Kathleen Graham
        Review newly submitted intakes under your area that need prioritization to be worked as a business case, prioritize that list, and get awareness of upcoming intake forms to be submitted
Key Dates for Next EIB Session

## Slide 11: Appendix

## Slide 12
Project Health
*Bold/green within next 90-day implementation window
Active Project Status Report

## Slide 13
Project Health
*Bold/green within next 90-day implementation window
Active Project Status Report

## Slide 14
90 Days to Implementation
All projects implementing prior to January 30, 2024
  OHR Look Behind 10/31/23 - On track after CAB approval
    Security ATO and business have signed off, CAB approval should be 11/7/23
Forensic Information Management System (FIMS) 10/31/23 will be 11/3/23
  3 records prod records being validated, remaining will load upon validation
  Application Reduction Initiative 12/29/23
    On track to complete on time
  EHR Enterprise Dragon Medical One 12/29/23
    On track to complete on time
  Glucose Monitoring 12/29/23 - postponed, on hold
    No Point of Care Coordinator. Go live date depends upon new hire
Grant Management 12/31/23
    On track to complete on time
CBORD Phase 1 1/17/24
  May push until 2/1/24 due to resource constraints and holiday vacation schedules
7 projects within 90-day implementation window

## Slide 15
Project NOT Green
VCC
  Developed Draft plan for mobile dispatch training/qualification, reviewing with business
  Path to Green: Flush out details in SOW for secured sole vendor, align to budget, and update implementation plans
CBORD NetMenu
  Contract disputes, increased costs and delays, revising project schedule
  Path to Green: Adjusting schedule for comparison activities and parallel validations
Data Exchange CCS3 Sunset
  Realized risk of EDW vendor contract negotiations delaying the schedule.
  Path to Green: Expediting the RFP process and finalizing the data elements for the integration solution with CSB EHR
Revenue Cycle Modernization
  Avatar replacement: revising RFP based on VITA feedback, arranging demo of the Cerner Registration system
  Path to Green: Need to align comprehensive goals for the project with leadership and business strategy
  Glucose Monitoring
    Resource constraints: Business lead requested to postpone the Go Live date; no Point of Care Coordinator identified
    Path to Green: Project team completing Go Live readiness assessment; facility services team addressing POC Coordinator
  Omni Cell
    New solution and new vendor required; VITA set up a pre RFS meeting coming Wednesday to review technical requirements
    Path to Green: Project will be on hold for month or two until we finalize path forward, rescoping project
  OHR Look Behind
    UAT testing and Security ATO complete CAB approval should be 11/7/23
    Path to Green: Await CAB approval and move to production
7 Projects off track