## Slide 1: Enterprise Investment Board
January 2024 Monthly Meeting

## Slide 2
A Very Happy New Year To Everyone !
Establish Quorum
Review Action Items
Celebrate Success(es)
Intakes & EPMO Recommendations
Decisions from EIB
Q&A Interactive Session
Appendix – Project Health
Agenda

## Slide 3: Celebrate Success
This month has seen continued optimization of the process to address intakes in a timelier fashion.
The involved personnel have proven to bring value to the efforts underway, thereby solidifying the team for future success.
The funneling of requests through the “One-Stop Shop” is continuing to show immense value in terms of visibility and consolidation of investments.
Continued support of the Senior Leadership Team has been invaluable for providing direction and structure to meet the dynamic needs of our Agency.
Recent Successes

## Slide 4: Intake Pipeline (32)
Open ITIB Submissions (7)
Elavon (electronic payments)
Web Portal for Marcus Alerts
Facilities Enterprise Human Resource System Solution (formerly HOPS HR)
Fiscal Note/Fireside Chat
ObservSMART
EDCC Integration
Discharge Assistance Planning
Potential Future Projects List
Grandfathered in – No Intake Form (3):
AAIDD/Supports Intensity Scale
Counter Tools
VA Navigator
Microsoft Power BI (powerbigov.us)
Open EIB Submissions (29)
Closed (3)
Business Case Backlog

## Slide 5
New Intakes
 | Name of Request | Status
Facilities / Clinical | DBHDS Public Safety Application: Omnigo | Ready for EIB approval
 | SynMed (contract renewal) | Ready for EIB approval
 | Facilities EHR OnePlan (Treatment Planning) Beta Partnership | Ready for EIB approval
Operations | HowSo; Formerly DivePlane | Pre EIB Lead Review
 | Replace Little CARS Database | Pre EIB Lead Review
Community | CAI Staff Augmentation for IMS Replacement/Legacy Systems Data; Analysis and Migration | Ready for EIB approval
 | Central Registry for Opioid Treatment Providers (OTP) | Ready for EIB approval
New Intakes (7) to be reviewed in January

## Slide 6: Upcoming Intakes
Potential Future Projects List
Potential Intakes where Submissions have not yet been made (6)
Tickit Health
EHR – ADC and Integration w/ EHR Catawba and SEVTC
Update legal status code in Avatar
EHR - Oracle Millennium (Mythics/CAI)
EHR - text communication with PHI
PM tool (ex. Sensei IQ vs JIRA)

## Slide 7: Next Step – Revisit
EPMO Recommendation
ObservSmart:
  During the 12/14/23 Facilities Enterprise Technology Collaboration meeting, it was proposed to combine the business needs expressed in the intakes for Patient ID Armband Integrated Solution and ObservSMART into a single intake, with the potential result to allow for ObservSMART at some facilities and Patient ID Armband at other facilities to accommodate the different business needs of each facility.
  Different facilities are inclined towards one or the other solution.
    Facilities have expressed issues with the armbands in terms of ease of damage / removal and erroneous exchangeability amongst individuals.
    Some facilities do not want either solution.
  EPMO Recommends to combine both requests to:
    Effectively solve disparate needs of facilities
    Demonstrate that an enterprise solution can be a combination of solutions potentially.

## Slide 8: Next Step – Close
Recommendations to Close
Renewals for existing contracts
Reviewed by BA for completeness
PM/Intake Lead has addressed all VITA needs where warranted
Community | Clinical/Facilities | Operations (3)
 |  | Gartner Consulting Services
 |  | Sensei Subscription Renewal
 |  | HowSo/Diveplane
Notes: Gartner –
  Recommending for closure.
  Budget Cuts affected the renewal of the Gartner Services.
  No work remaining for Intake Services to do and IT has all the approvals needed in case funding is received.
Sensei -
  Amount of money below the threshold, no CTP needed.
HowSo -
  No PGR amendment needed.
  Requisition to be submitted – ensure this is done

## Slide 9: Next Step – Approve for Project
Recommendations to Project
Community | Clinical/Facilities | Operations
None | None | None

## Slide 10: In Progress – Business Case Development (10)
Progress Update
Unfunded
Community (1) | Clinical/Facilities (7) | Operations (2)
CAI Staff Augmentation for IMS Replacement/Legacy Systems Data; Analysis/Migration Prep | Language Interpretation & Translation Solution | EDCC Integration / Smartchart Network
 | Facilities Clocks & Badges Replacement | Waystar ECOS Assessment
 | UKG Dimensions/Pro Migration & Implementation | 
 | Patient ID Armband Integrated Solution | 
 | ePrescribe Discharge Medication Billing | 
 | Discharge Assistance Planning (DAP) | 
 | Telehealth Services | 

## Slide 11: Next Step – Start Business Case Development (14)
EPMO Pipeline Backlog
Unfunded
Community (1) | Clinical/Facilities (7) | Operations (5)
Central Registry for Opioid Treatment (OTP) | DBHDS Public Safety Application: Omnigo (remaining facilities) | Financial Management System
 | SynMed (contract renewal) | Enterprise Human Resource Information System Solution
 | Facilities Enterprise Vital Signs Integration | Fiscal Note/Fireside Chat
 | Cashless Payment Solution (VCBR) | Elavon (electronic payments)
 | OSVP Database | Replace Little CARS Database
 | MART Master Scheduler | 
 | Facilities EHR OnePlan (Treatment Planning) Beta Partnership | 

## Slide 12: Next Step – Pre-EIB Request Review
Intakes Submitted After EIB Deadline
Community | Clinical/Facilities | Operations
 | OnShift ECOS | 

## Slide 13: Coming Soon………. EIB Process Enhancements
The Future is Now
The folks at the EPMO ‘Skunkworks’* have been thinking and talking
We want to enhance and improve the process
That’ll make us COOL like these guys !
So that we can:
more intakes faster.
Introduce a FastTrack (Case By Case basis) Model.
Utilize / Repurpose existing resources, or add new resources as needed.
Reduce SLAs for a timelier delivery
Assess Autonomy for certain types of intakes.
…… and more to be introduced in the next session.
Process

## Slide 14
Active Projects – Change Request
Pyxis ADC Project Change Request
  Due to Omnicell Modernization project closure, include Omnicell facilities within scope
  of BD Pyxis Project
  Recommendation: Increase scope of existing project to include facilities approaching
  end of life with Omnicell that were covered under the now closed Omnicell
  Modernization project, as well as any facility not covered under either project
  (Example: Catawba)
Pyxis ADC Project Sponsor Guidance
  There is an immediate need to standardize the enterprise management of the root pharmacy formulary and management of the nursing related configuration, rules and parameters. Decisions are needed to progress the project and for O&M this will be ongoing. Project cannot be executed effectively without the roles below.
  Recommendation:
    Assign or hire a centralized pharmacy system administrator immediately
    Assign or hire a centralized nursing system administrator immediately

## Slide 15: February EIB Meeting Tuesday, 02/13/2024
01/29/2024 EIB Submission Form Deadline
01/31/2024 EIB / Data Modernization Program Sync Up w/Kathleen Graham
        Review new intakes submitted across the agency for data modernization program alignment (to pursue great on future state vs better on current state)
01/30/2024 EIB Priority List for Jan EIB (Community) w/Margaret Steele and Jean Dailey
01/31/2024 EIB Priority List for Jan EIB (Facilities/Clinical) w/Lauren Cartwright and Charles Mathenge
01/31/2024 EIB Priority List for Jan EIB (Operations) w/Russell Accashian and Kathleen Graham
        Review newly submitted intakes under your area that need prioritization to be worked as a business case, prioritize that list, get awareness of upcoming intake forms to be submitted, bring awareness to any scope/schedule/budget change requests for active approved projects
Key Dates for Next EIB Session

## Slide 16: Appendix

## Slide 17
*Bold/green finish days due to complete within next 90 days
Project Health
Active Status Report 12-15-23

## Slide 18
*Bold/green finish days due to complete within next 90 days
Project Health
Active Status Report 12-15-23

## Slide 19
90 Days to Implementation
All projects implementing prior to March 12, 2024
  Three projects green, to complete on time by 12/29/23
  TRAC-IT Phase 2
    Go-Live scheduled 12/11/23
  Application Reduction Initiative
Grant Management Phase II
  One project at risk (details on slide 6)
    Glucose Monitoring Go-Live postponed, on hold
4 projects within 90-day implementation window
In Production

## Slide 20
Project NOT Green
VCC
  Mobile Dispatch training is complete
  Path to Green: Create a change request through VITA
    Complete new contract with Behavioral Health Link
    Identify scope/schedule/budget changes and submit to VITA the change request
  Upcoming Milestones:
    Complete Readiness Checklist for re-launch to go in PROD by December 15th
    Mobile Dispatch Go-Live December 16th
    Execute emergency contract and SOW for subscription by December 31st
CBORD NetMenu
  Preload activities now 96% complete; 4 facilities remaining
  Path to Green: Adjust schedule in Planview for delays and scope decision by December 18th
  Upcoming Milestones:
    Facilities complete go-live checklist by December 8th
    PROD migration occurred or critical bug fix December 8th
    Part 2 of identifying critical EHR and interface issues by December 13th
    Evaluate go-live readiness by December 18th
    Resolve all critical issues during Dec window December 9th – 19th
7 Projects
off track
2 of 7

## Slide 21
Project NOT Green
Data Exchange CCS3 Sunset
  Realized risk of EDW vendor contract negotiations delaying the schedule
  Path to Green: Determine changes to schedule after EDW vendor finalized
  Upcoming Milestone: Finalize Spec document by December 31st (not impacted by risk)
Revenue Cycle Modernization
  Final RFP package submitted to VITA December 6th
  Path to Green: VITA reviewed early and will share results with agency next week
  Upcoming Milestone: Publish RFP in eVA by December 22nd
Tracers with AMP Plus CMS
  Procurement to advise of contract approval status
  Path to Green: Obtaining fully executed contract
  Upcoming Milestone: Meeting with Business Owners to review Stakeholder Register by December 15th
3 of 7
7 Projects off track

## Slide 22
Project NOT Green
  Glucose Monitoring
    Go-Live postponed, Project Sponsor made decision to perform Path to Green activities​
    Path to Green:
      Project Sponsor assign a Business Owner and hire a Point of Care Coordinator
      PM adjust required deliverables and implement mitigations for identified risks
    Upcoming Milestones:
      Presentation outlining gaps and constraints to Executive Sponsor December 11th
      Sponsor will assign new Business Owner or a timeline by the January 9th EIB Meeting
      Business Owner will verify Point of Care Coordinator is hired by end of January
  OMNICELL Modernization
    OMNICELL solution no longer feasible – EIB intake form submitted to address need
    Path to Green: ​N/A – Project cancelled
    Upcoming Milestones: Project closeout by January 12th
2 of 7
7 Projects off track