## Slide 1: Enterprise Investment Board
February 2024 Monthly Meeting

## Slide 2
Establish Quorum
Review Action Items
Celebrate Success(es)
Progress Updates, New Intakes & EIB Decisions
Clinical / facilities Gantt chart review
EIB Retrospective
Q&A
Agenda

## Slide 3: Celebrate Successes
Defined criteria for:
  what Intake Services team must do to hand off the Business Case to the Project Delivery team
  what happens during the handoff meeting between the Intake Services team and the newly assigned Project Manager
  what the PM initially must do following the handoff meeting
  how long the Intake Services team is available for consults if questions arise (30 calendar days)
3 Business Cases Completed: E-Prescribe, Waystar ECOS, Synmed Contract Renewal
Launched the EPMO Governance Model 1.0
Instituted a weekly review session for off track projects. Attended by Business leads, Project Managers, Business Owners, and Andrew Diefenthaler
Established a collaborative working group that includes the Clinical / Facilities Business leads, the Project Management team, and Enterprise Application IT Team.
  drafted the change control process.
  drafted and reviewed roles and responsibilities for Accountable Executives (A.E.)
Recent Wins

## Slide 4: Intake Pipeline (35)
Potential Future Projects List
Microsoft Power BI (powerbigov.us)
Open Submissions (30)
  Active (25)
  Pending (2)
  On Hold (3)
Closed (5)
Business Case Backlog

## Slide 5: Progress Updates, New Intakes & EIB Decisions

## Slide 6: In Progress – Business Case Development (8)
Progress Update
Community (1) | Clinical/Facilities (6) | Operations (1)
Central Registry for Opioid Treatment Providers (5%) - (R-20) | Language Interpretation & Translation Solution (100%) – remove? (R-2) | EDCC Integration / SmartChart Network (5%) (R-12)
 | UKG Dimensions/Pro migration & implementation (60%) (R-7) | 
 | Patient ID Armband Integrated Solution (70%) (R-10) | 
 | E-Prescribe Discharge Medication Billing (100%) (R-13) – BC complete | 
 | Discharge Assistance Planning (DAP) (30%) (R-15) | 
 | Telehealth Services (60%) (R-17) | 

## Slide 7
New Intakes
New Intakes (2) to be reviewed in February against current priorities
Approve for Business Case?
Community (1) | Clinical/Facilities (1) | Operations (0)
WaMS CR-141 Multi-Factor Authentication (R-3) | OnShift ECOS (R-8) | 

## Slide 8: Next Step – Close
Recommendations to Close
Community (1) | Clinical/Facilities (0) | Operations (2)
IMS – CHRIS Data Cleanup Procurement of resources in progress | None | Synmed Contract Renewal
 |  | Waystar ECOS Assessment
Notes: Gartner –
  Recommending for closure.
  Budget Cuts affected the renewal of the Gartner Services.
  No work remaining for Intake Services to do and IT has all the approvals needed in case funding is received.
Sensei -
  Amount of money below the threshold, no CTP needed.
HowSo -
  No PGR amendment needed.
  Requisition to be submitted – ensure this is done

## Slide 9: Next Step – Approve for Project (1)
Project Recommendations
Community (o) | Clinical/Facilities (0) | Operations (1)
None | None | Fast Track Project – Little Cars Data Update (R-3)

## Slide 10: March EIB Meeting Tuesday, 03/12/2024
02/20/2024 EIB Submission Form Deadline
02/29/2024 EIB / Data Modernization Program Sync Up w/Kathleen Graham
        Review new intakes submitted across the agency for data modernization program alignment (to pursue great on future state vs better on current state)
02/28/2024 EIB Priority List for Mar EIB (Community) w/Margaret Steele and Jean Dailey
02/29/2024 EIB Priority List for Mar EIB (Facilities/Clinical) w/Lauren Cartwright and Kylie Robbins
02/29/2024 EIB Priority List for Mar EIB (Operations) w/Andrew D. and Kathleen Graham
        Review newly submitted intakes under your area that need prioritization to be worked as a business case, prioritize that list, get awareness of upcoming intake forms to be submitted, bring awareness to any scope/schedule/budget change requests for active approved projects
Key Dates for Next EIB Session

## Slide 11
Previous decisions
January Intakes Statuses – Any changes needed to “On Hold”
Community (1) | Clinical/Facilities (2) | Operations (1)
None | Facilities EHR OnePlan (Treatment Planning) Beta Partnership (R-4) – On Hold | Replace Little CARS Database (R-21) – Preceded by Little CARS Data Update – On Hold
 | DBHDS Public Safety Application: Omnigo (R-8) – On Hold | 
Hold – No action / analysis since last EIB session

## Slide 12: Appendix

## Slide 13: BACKLOG (Pending BA assignment for Business Case Development)
EIB Business Case Backlog
Unfunded
Community (0) | Clinical/Facilities (4) | Operations (4)
None | Facilities Enterprise Vital Signs Integration (R-16) | Financial Management System (R-18)
 | Cashless Payment Solution (VCBR) (R- 25) | Enterprise Human Resource Information System Solution (R-22)
 | OSVP Database (R- 30) | Fiscal Note/Fireside Chat (R-23)
 | MART Master Scheduler (R- 29) | Elavon (electronic payments) (R-27)

## Slide 14
  Gantt chart addresses
    end of life concerns,
    known dependencies,
    end user groups/project team members required for project effectiveness;
    which efforts are behind and
    begins to establish an approach and timeline for EIB to course correct, sequence efforts, and/or reject intakes to be worked.
  HOWEVER…
  Engagement with facilities on existing projects is not at a level needed to ensure successful outcomes to operations.
  Moving forward without addressing operational barriers poses a risk to effectively deciding priorities, sequence activities, and ultimately successfully implementing projects.
  If we accept this risk, there are things we can do right now to still move forward.
Disclaimer

## Slide 15
  *Heavy demands on Facility Nursing, Facility IT, and CO IT across majority of efforts requires additional sequencing to support patient care & safety and mitigate risk to project schedules!
  By further reducing the number of concurrently worked projects, facility and CO staff can more fully engage and participate in the chosen efforts leading to projects completing faster, with lower costs, and with solutions that truly meet business needs!
Gantt exceeds saturation points and will require additional resources:
  ISO: max 3 concurrent projects/person
  EPMO: max 2 concurrent projects/person (unless VITA Category limits PM to 1)
  Procurement: max 2 RFPs + 1 SS/procurement officer
  Facilities: TBD
Appendix
  Operational Barriers
  Risks
  Known Dependencies
  Highly impacted groups by project
  Heavy demands on Facility Resources
  Additional Resources required to support Gantt chart timeline
  Lessons Learned – Business Cases
  Wins and Successes
Where we are today

## Slide 16
Complete review underway of already approved projects not led (and led) by Clinical/Facilities
  to identify in what areas the engagement is lacking,
  who would be the best resource(s) to participate based on the timeframe for the specific activity(ies) outlined in project schedule(s),
  how much time would they need to devote
  THEN see if there are resources available at CO and facilities to start new efforts within scope of the Gantt chart.
On 2/14/24: Angela H. to engage Facility Directors to identify saturation point by facility and discuss Gannt chart achievability
Use existing funding for immediate resource needs.
  PM for UKG Workforce Pro
  Extend funding for PM (Jeannette) through FY24.
  Extend funding for PM (Quanya) through FY24.
Immediate Next Steps
#1 Priority

## Slide 17
Next Steps
  To support the Enterprise Policy Management System Performance Improvement Effort,
  Lauren C. and Andrew C. have started determining if a policy (and related process, procedures, DIs) exists related to the efforts in scope of the Gantt chart. Facility policy template has not been finalized.
  Prioritize policy review and creation of general CO policies that can be expanded at the facility level (and related process, procedures, DIs) related to these efforts to ensure adoption, standardization, and compliances are met.
  As part of the project, update the applicable policy as the project goes through execution, if needed.
  EPMO Intake Services is also adding a question into the intake form: List any Policies associated with this request (within PowerDMS or externally such as The Joint Commission)

## Slide 18
Effort | FY 2024 | FY2025 | FY 2026
Enterprise Policy Management System Performance Improvement Effort |  |  | 
Electronic Requisitioning for all state facilities in eVA (+the eVA interface for food services) |  |  | 
Facilities Clock and Badge Replacement (CSH, ESH, SWVMHI, CCCA, SEVTC, NVMHI, HDMC) |  |  | 
Facilities Enterprise Kronos/UKG Workforce Pro Central and Advanced Scheduling Replacement (SS) |  |  | 
Pyxis ADC Integration with EHR (ESH, HDMC (so also CSH), NVMHI, SWVMHI, VCBR) = Phase 1 |  |  | 
Patient ID Armband Integrated Solution (all facilities) |  |  | 
Revenue Cycle Modernization (+ MAYBE ePrescribe Med Billing) |  |  | 
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Today
Planning
Initiation
Pre-Initiation
Execution
Closing & Archiving
L
L
Q&Cr
N
PM
L&O Phase 1
O
Q&N
C&V
Jan 24
Jan 25
Jan 26
Phase 2 TBD
PM
Phase 3 TBD
E
ISO needed
Behind
Off track

## Slide 19
Effort | FY 2024 | FY2025 | FY 2026
Oracle Millennium (vs. Mythics/CAI) new SS contract |  |  | 
TRACERS with AMP Plus CMS |  |  | 
Facilities EHR OnePlan (Treatment Planning) Early Adoption Partnership |  |  | 
Glucometer Monitoring Integration (CSH, ESH, HDMC, NVMHI, SVMHI, SWVMHI, WSH) |  |  | 
Incident Management System (RFP) |  |  | 
Telehealth Services for State Facilities (ties with revenue cycle) |  |  | 
Facilities Language Interpretation and Translation Solution (+ECOS) |  |  | 
Discharge Assistance Program (DAP) (method of procurement unknown) |  |  | 
Smartchart Network / EDCC Integration DBHDS and CSB EHRs (top solution dep. on EDW go live) |  |  | 
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Today
Planning
Initiation
Pre-Initiation
Execution
Closing & Archiving
Q &N
P
Sr. PM
O
Cr
T&Ch
PM
E
V
S
K
Jan 24
Jan 25
Jan 26
I&Cr
J
J
J
PM
ISO needed
Behind
Off track

## Slide 20
Effort | FY 2024 | FY2025 | FY 2026
Facilities Enterprise HRIS (no funding) (method of procurement unknown) |  |  | 
FMS Replacement (method of procurement unknown) |  |  | 
DBHDS Public Safety App: Omnigo (3) |  |  | 
OnShift ECOS |  |  | 
EDM Patient eSignature |  |  | 
Facilities Enterprise Vital Signs Integration (VCBR –not enterprise solution need 7500) |  |  | 
CBORD NetMenu |  |  | 
Virginia Crisis Connect |  |  | 
Data Governance |  |  | 
EDW Modernization |  |  | 
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Planning
Initiation
Pre-Initiation
Execution
Closing & Archiving
Jan 24
Jan 25
Jan 26
James 4 schedule
Henry 4 schedule
L&V
S
Q&N
Q &N
Q
N
S
PM
BA
PM
Today
BA
ISO needed
Behind
Off track
PM
John 4 schedule

## Slide 21
Effort | FY 2024 | FY2025 | FY 2026
OSVP Database (method of procurement unknown) |  |  | 
Cashless Payment Solution (VCBR) (method of procurement unknown) |  |  | 
Elavon expansion to entire Agency (Electronic Payment Process for Patient Payment) |  |  | 
Dragon Medical One |  |  | 
SynMed (contract renewal) |  |  | 
Safety and Attendance (no priority or rank as of 2/6) |  |  | 
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Q4
Q3
Q2
Q1
Today
Planning
Initiation
Pre-Initiation
Execution
Closing & Archiving
Jan 24
Jan 25
Jan 26
N
PO
K
BA
BA
PM
PM
BA
PM
ISO needed
Behind
Off track

## Slide 22
    There is a lack of clear understanding of operational structure across the agency. Level of autonomy and decision-making responsibilities of separate business units is not well defined.
    Similarly-sized facilities have different departmental staff head counts, vacancies, working and role titles, and budget allocations within “business units”, as well as different technology infrastructure.
    There is a lack of a target operating model to drive the business strategy for data integration and process standardization across business units.
    Addressing barriers above is needed prior to being able to effectively decide priorities and sequence activities, and ultimately the successful implementation of projects.
Major Issue - Operational Barriers

## Slide 23: Appendix

## Slide 24
    Operational barriers make it difficult to decide priorities, which impacts how efforts are sequenced.
    Low coordination of facility projects and initiatives not managed by EPMO
      Access Control priority over Clock and Badge replacement
      Application Lifecycle Management, i.e. application retirements and associated efforts
    Gantt fails to consider efforts not impacting Clinical/Facilities that require Procurement and other CO staff.
    If efforts where procurement method is unknown requires an RFP, additional procurement resources will likely be needed.
    May need additional resources based on completion of business cases.
Risks

## Slide 25
Known Dependencies
Technology Dependency
Facilities Clock and Badge Replacement (CSH, ESH, SWVMHI, CCCA, SEVTC, NVMHI, HDMC) before Facilities Enterprise Kronos/UKG Workforce Central and Advanced Scheduling Replacement.
Electronic Requisitioning for all state facilities in eVA including the eVA interface for food services to reduce manual process of managing inventory for CBORD NetMenu.
CBORD NetMenu (facilities already using CBORD) before VCBR Adoption of CBORD NetMenu.
EDW go-live before EDCC Integration
Patient Safety Risk / End of Life Dependency
Pyxis ADC Integration with EHR at ESH, HDMC (so also CSH), NVMHI, SWVMHI, VCBR before SVMHI, WSH, CCCA, and PGH before Catawba and possibly SEVTC. New CSH phase to be determined.
Procurement Dependency
Oracle Millennium Sole Source contract (current SOW ends Aug 2025) before Telehealth Services for State Facilities
Data Dependency
IMS Replacement/Legacy Systems Data; Analysis/Migration Prep before Incident Management System implementation
Resourcing Dependency
Pyxis ADC Integration with EHR before ePrescribe Medication Billing for ESH.
See next slide for overlapping resources. Providers, HIM, Social Work, quality and compliance, and other clinical staff also are impacted with multiple projects.

## Slide 26
Facility Training Staff & Facility IT Staff | Facility Nursing Staff | CO IT | Clinical Informaticists
All | Pyxis ADC Integration with EHR | Pyxis ADC Integration with EHR | Pyxis ADC Integration with EHR
Facility & CO Finance | Facilities EHR OnePlan (Treatment Planning) Early Adoption Partnership | Facilities EHR OnePlan (Treatment Planning) Early Adoption Partnership | Facilities EHR OnePlan (Treatment Planning) Early Adoption Partnership
Facilities Enterprise UKG Dimensions/Pro - Migration and Implementation | Facilities Enterprise Kronos/UKG Workforce Central and Advanced Scheduling Replacement | IMS Replacement/Legacy Systems Data; Analysis/Migration Prep and Incident Management System | 
Electronic requisitioning in eVA for all facilities |  | Electronic requisitioning in eVA for all facilities | 
Facilities Enterprise Human Resource Information System Solution | Facilities' Patient Identification Armband Integrated Solution | Facilities' Patient Identification Armband Integrated Solution | Facilities' Patient Identification Armband Integrated Solution
ePrescribe Discharge Medication Billing | ePrescribe Discharge Medication Billing | ePrescribe Discharge Medication Billing | ePrescribe Discharge Medication Billing
Telehealth Services for State Facilities | Telehealth Services for State Facilities | Telehealth Services for State Facilities | Telehealth Services for State Facilities
Financial Management System Replacement | Smartchart Network / EDCC Integration | Smartchart Network / EDCC Integration | Smartchart Network / EDCC Integration
Revenue Cycle Modernization | Revenue Cycle Modernization | Revenue Cycle Modernization | 
 | Facilities Enterprise Vital Signs Integration | Facilities Enterprise Vital Signs Integration | Facilities Enterprise Vital Signs Integration
 | Facilities Language Interpretation and Translation Solution | Discharge Assistance Planning (DAP) | 
 | EDM Patient eSignature | EDM Patient eSignature | EDM Patient eSignature
 | Glucose Monitoring (Glucometer) | Glucose Monitoring (Glucometer) | Glucose Monitoring (Glucometer)

## Slide 27
Functional Area | Position | Hire by: | Project Name | Est. Funding
EPMO | Project Manager 4 ($125.06/hr) | Immediately | UKG Workforce Pro | FY24: FY25: FY26:
EPMO | Project Manager (Jeannette) | Extend funding | DAP (or higher priority assigned project) | FY24: FY25:
EPMO | Project Manager (Quanya) | Extend funding | Patient ID Armband & Glucometer | FY24: FY25:
EPMO | Business Analyst (Nancy) | Extend funding |  | FY25:
EPMO | Project Manager 3 ($120.35/hr) | 7/1/2024 | Pyxis ADC Integration with EHR (Phase 2&3) | FY25: FY26:
EPMO | Project Manager 2 ($115.72/hr) | 7/1/2024 | Facilities EHR OnePlan (Treatment Planning) Early Adoption | FY25:
EPMO | Business Analyst 4 ($85.32/hr) | 3/15/2024 |  | Fy24: FY25:
Additional Resources Needed
Can be populated once final sequencing is known.

## Slide 28
Functional Area | Position | Hire by: | Project Name | Est. Funding
EPMO | Project Manager 2 ($115.72/hr) | 9/15/2024 | Telehealth Services for State Facilities | FY25:
EPMO | Project Manager (Quanya) | Extend funding | EDM Patient eSignature & Enterprise Vital Signs Integration | FY26:
EPMO | Business Analyst (Nancy) | Extend funding |  | FY26:
ISO | 2 ISO ($95/hr ea) (Shina & Amanda) | Extend funding | 3 projects max/ISO | FY25: $364,800 FY26: $364,800
EPMO | Project Manager 2 ($115.72/hr) | 4/1/2024 | Omnigo | FY24: FY25:
Additional Resources Needed
Can be populated once final sequencing is known.
TBD

## Slide 29
Functional Area | Position | Hire by: | Project Name | Est. Funding
EPMO | System Analyst 4 ($104.09/hr) | 7/1/2024 | FMS Replacement | FY25: FY26:
EPMO | Project Manager 4 ($125.06/hr) | 9/1/2024 |  | FY25: FY26:
EPMO | System Analyst 4 ($104.09/hr) | TBD based on final sequencing | Facilities Enterprise HRIS | FY25: FY26:
EPMO | Project Manager 4 ($125.06/hr) | Enterprise solution w/ FMS? |  | FY25: FY26:
EPMO | Project Manager 2 ($115.72/hr) | 9/1/2024 | OSVP Database & Cashless Payment Solution (VCBR) | FY25:
EPMO | Business Analyst 4 ($85.32/hr) | 7/1/2024 |  | FY25:
ISO | ISO(s) | TBD based on final sequencing | 3 projects max/ISO | FY25: FY26:
Additional Resources Needed
Can be populated once final sequencing is known.

## Slide 30
  The Benefits and Risks section in the Business Case serves as a valuable tool for business owners to anticipate gains, guide projects, and assess post-implementation impact to determine to what extent the change led or did not lead to an improvement.
  For the Dragon Medical One (DMO) project, we could know if the change led to an improvement by considering rate of use (process metric), time in the EHR pre- and post- data from the Oracle Advance tool (outcome metric), and end-user satisfaction (outcome metric). These metrics offer insight into the impact of this project in furthering the organization’s strategic goals (KR8a) and vision. Dr. DeSouza requested CIs leverage DMO usage reports to track user engagement with the solution, aiming to understand and address any low usage issues through awareness and education campaigns.
  This section, when considered alongside estimated costs, aids the EIB in deciding whether the identified risks are worth the anticipated benefits. Redefining proposed solutions can streamline Business Case production for Intake Services, maintaining focus on measurable benefits and risk awareness. This aspect, lacking in the ITIB concept/transition document, offers an additional area where the EIB Business Case can benefit the agency.
Lessons Learned – Business Cases

## Slide 31
  Cross-division review of current state meeting register of OKR 8b related meetings
    Change Advisory Board membership and scope expanded to incorporate EA and EPMO
    Establishment of Weekly Portfolio Management meeting for Clinical/Facilities
    EPMO, IT EA and O&M, Facility Services Division Admin and Quality work sessions targeting process improvements, communication plans, role definitions and relationships
    Clinical/Facilities EPMO Interim Sr. PM in weekly EHR Strategy meeting for alignment on EHR roadmap
Wins and Successes